## Gantt Box Chart
Gantt Box Chart - Template
Task | Start | Best Case | Realistic | Worst Case | BC | R | W
Project Kickoff | 2010-06-01 | 2010-06-05 | 2010-06-09 | 2010-06-14 | 4 | 4 | 5
Gather Requirements | 2010-06-06 | 2010-06-13 | 2010-06-18 | 2010-06-23 | 7 | 5 | 5
Design Module 1 | 2010-06-11 | 2010-06-17 | 2010-06-20 | 2010-06-27 | 6 | 3 | 7
Design Module 2 | 2010-06-11 | 2010-06-16 | 2010-06-19 | 2010-06-26 | 5 | 3 | 7
Develop | 2010-06-20 | 2010-06-29 | 2010-07-15 | 2010-07-22 | 9 | 16 | 7
Test | 2010-07-21 | 2010-07-27 | 2010-07-29 | 2010-08-05 | 6 | 2 | 7
Implement | 2010-08-08 | 2010-08-14 | 2010-08-16 | 2010-08-23 | 6 | 2 | 7
Formulas:
Worst Case = [Realistic]+7
Best Case = [Start]+6
Realistic = [Best Case]+2
Start = [Worst Case, row above]+3
Chandoo.org
FREE Newsletter
How to use this?
1) Set up your project plan using the table in row 6
2) Just enter first 5 columns of dates
3) Last 3 columns are calculated. Do not mess with them.
4) If you have Excel 2007 or above, the calculated columns should automatically update when you add new rows to the table.
6) The chart now shows the project plan as a Gantt Box Chart
7) Adjust horizontal / date axis scaling and major units to see dates clearly.
For more info. visit:
http://chandoo.org/wp/2010/07/09/gantt-box-chart-proposal/
http://chandoo.org/wp/2010/07/12/gantt-box-chart/